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18.10.2026

Disraeli Opportunity Bucks Action Plan 2025/26

Community Focus leads: 	Gail Hudson

Ward partnership officer: 	Jackie Binning


Ward action plan development 

The Disraeli Ward Partnership have been working together to identify key stakeholders and key areas of focus for the next 12 months to develop their local action plans. The plan below is the result of two patch meetings held on 23rd July and 13th August 2025, alongside separate discussions with the Ward Councillor (Mazamal Hussain) and his engagement with residents. These outline their top priorities and ambitions for improving the place and opportunities for people who live in their ward. Alongside developing initiatives to address these priorities with local partners and communities, the ward partnership will continue to engage with their community to further understand resident and partner views, strengths and challenges which will further inform the development of local initiatives and ward action plans. 

Local Ward Partnership Action Plans demonstrate the progress of the priorities and project deliverables.

Alongside the priorities, the ward partnership will be instrumental in supporting community clean ups and Community Action days. 


	Ward Priority
	Purpose and Initiative
	Associated Theme
	Project Idea(s)

	To improve Traffic and Road issues

	Road safety is critically important because it protects lives, promotes wellbeing, and supports the smooth functioning of communities. The Ward plan to work in partnership with the Highways Authority and Parking Services Team at Buckinghamshire Council, to deliver infrastructure improvements and traffic calming measures in the areas identified.
	Quality of the Public Realm
	[bookmark: _Hlk219210934]To seek agreement with the Highways Authority on suitable traffic calming measures to address speeding concerns on Hughenden Avenue, and to approve the installation of yellow lines at the corners of Brindley Avenue, Brunel Road, Kevin Close, and Fulton Close to prevent vehicle parking that creates blind spots for other motorists.

Proposed completion date: 31.03.26
Update: The double yellow lines on the four corners detailed above have been approved – a date for the lineage work is to be agreed. 
Traffic Calming measures still be be addressed on Hughenden Avenue.

	To enhance the management and resolution of abandoned motor vehicles.
	Abandoned vehicles pose a range of challenges impacting community safety, environmental quality, and public perception. We aim to collaborate with the Waste Team at Buckinghamshire Council and Thames Valley Police to implement effective solutions and establish clear procedures for managing this issue within the area.
	Quality of the Public Realm
	To address the issue concerning a car, van, or other motor vehicle that has been left unattended for an extended period and appears to have been abandoned by its owner. To collaboratively agree on a framework that guides the development and delivery of effective solutions.

Proposed completion date: March 2027
Update: A “Vehicles of Concern” project is well underway and is being progressed by the Quality of Public Theme Group.

	To create a safer and more attractive environment along Hughenden Boulevard.
	Making public spaces safe and visually appealing is important for reasons such as social, environmental, economic, and psychological.
To work closely with partners to enhance both the safety and visual appeal of the footpath, River Wye and verge along Hughenden Boulevard. 
	Quality of the Public Realm
Health and Wellbeing
	To work in partnership with the Community Safety and Waste teams at Buckinghamshire Council, along with external stakeholders (including local schools and community groups) to co-develop a sustainable proposal that improves footpath safety and enhances the natural beauty of the River Wye and the adjacent verge owned by Buckinghamshire Council.

To enhance the verge owned by Buckinghamshire Council, running alongside the footpath, and create a more enjoyable space for residents to experience the River Wye and surrounding nature. Agreement would need to be sought from the Highways Authority.

Completion Day: May 2026
Update: The footpath and verge have been cleared, and the River Wye has been cleaned in collaboration with Ward Partnership stakeholders. Three benches have been installed along the verge.


	To empower young people through engagement, learning, and mentorship.
	Young people are at the heart of vibrant, resilient communities. By fostering meaningful connections, we can create spaces where they feel heard, valued, and empowered to grow. This priority focuses on engaging young people through inclusive, creative and inspiring opportunities that promote learning and personal development. 
	Health and Wellbeing
	Establish a partnership with Switch Lane CIC to develop a targeted initiative with Year 6 children at Disraeli School, aligned with their expressed priorities and broader youth needs.

Proposed completion date: December 2026
Update This project has been agreed between Disraeli School, Switch Lanes and the Ward Partnership, and will start on 19.10.26 for six weeks.

	Safeguarding the future of a key community asset

	A key priority in improving any community facility is ensuring that it remains safe, accessible, and fit for purpose for all who rely on it. Community buildings play an essential role in supporting social connection, education, wellbeing, and local services, so maintaining high‑quality, modern, and inclusive spaces is fundamental to their long‑term viability. 
	Health and Wellbeing
	The community facility at Vibe Church has been highlighted as an asset requiring urgent refurbishment work. A programme of refurbishment and improvement works have been identified. Upgrading critical infrastructure—such as roofing, accessibility features, heating, toilets, and safety systems—helps protect the building from deterioration, reduces future maintenance costs, and ensures that residents can continue to access valuable activities and support in a welcoming environment. Prioritising these improvements strengthens the resilience of the facility and ensures it can continue serving the community effectively for years to come.

Proposed completion date: January 2027
Update: This project has been approved and has commenced.
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A local response to Levelling Up




image1.png
Buckinghamshire R Fairhive ’ P ‘:m





image2.png
. . Eu:klnghamshlre py
Buckinghamshire LAY .
Council T Bkt oosnee )/‘:ﬁ M ‘Falrhlve k @




