18.10.2026

Totteridge & Bowerdean Opportunity Bucks Action Plan 2026/27

Community Focus leads: 	Gail Hudson

Ward partnership officer: 	Jackie Binning

Ward action plan development

The Totteridge and Bowerdean Ward Partnership have been working together to identify key stakeholders and key areas of focus for the next 12 months to develop their local action plans. The plan below is the result of the Ward Partnership meeting held on 8th June 2026. These outline their top priorities and ambitions for improving the place and opportunities for people who live in their ward. Alongside developing initiatives to address these priorities with local partners and communities, the ward partnership will continue to engage with their community to further understand resident and partner views, strengths and challenges which will further inform the development of local initiatives and ward action plans.

Local Ward Partnership Action Plans demonstrate the progress of the priorities and project deliverables.

Alongside the priorities, the ward partnership will be instrumental in supporting community clean ups and Community Activity days.

| Ward Priority | Purpose and Initiative | Associated Theme | Project Idea(s) | Proposed completion date | Actual completion date |
| --- | --- | --- | --- | --- | --- |
| To improve Traffic and Road Issues | Road safety is critically important because it protects lives, promotes wellbeing, and supports the smooth functioning of communities. The Ward Partnership will collaborate with Buckinghamshire Highways to consider infrastructure enhancements and traffic calming measures in the identified areas. | Health and Wellbeing Quality of the Public Realm | - A traffic island in Bowerdean requires with planters with compost and shrubs to complete an unfinished scheme . The traffic island was protected from parking but left a one meter strip due to utility risk assessment. - Bowerdean - Hatters Lane Hill and Totteridge Hill/Road require fixed solar powered SIDs (4 off) - low maintenance, durable, permanent fixture. - Knee rails/ bollards required at Walton Drive/ Hardenwaye Green. To prevent commercial fly tipping and car parking, to protect green area used by local residents. - Replace broken bollards and install new bollards throughout Totteridge. | 31.03.27 |  |
| To improve Traffic and Road Issues Cont’d | Road safety is critically important because it protects lives, promotes wellbeing, and supports the smooth functioning of communities. The Ward Partnership will collaborate with Buckinghamshire Highways to consider infrastructure enhancements and traffic calming measures in the identified areas. | Health and Wellbeing Quality of the Public Realm | - Bowerdean Crossroads require bollard on the NW corner due to persistent parking on the pavement. - Totteridge Green at Hardenwaye – require timber kneel raised to stop companies placing containers on green. - Hollis Road and Leas Close verge hardening and dropped kerbs – required due to anti -social parking which causes slip hazard. - Hollis Road and Leas Close verge hardening and dropped kerbs – required due to anti -social parking which causes a slip hazard. | 31.03.27 |  |
| To improve Traffic and Road Issues Cont’d | Road safety is critically important because it protects lives, promotes wellbeing, and supports the smooth functioning of communities. The Ward Partnership will collaborate with Buckinghamshire Highways to consider infrastructure enhancements and traffic calming measures in the identified areas. | Health and Wellbeing Quality of the Public Realm | - To install a railing along the public footpath at the junction of Gordon Road and Bowerdean Road, where vehicles have been parking. As the footpath is heavily used by pedestrians travelling to work, a railing of approximately 2–3 metres is proposed to help keep the area clear. - Knee Rails to prevent parking on green area in Totteridge Drive adjacent to shops. - Raised table for cycling and walking with crossing at Totteridge Lane between pharmacy and Totteridge Common in the popular conservation area. | 31.03.27 |  |
| Investing in Community Assets | Investing in community assets is important because it strengthens local areas by improving quality of life, supporting wellbeing, and creating spaces that bring people together. Well-maintained facilities, services, and shared spaces encourage social connections, boost local pride, and can stimulate economic activity, making communities more resilient and attractive places to live. The Ward Partnership will review this infrastructure enhancements and collaborate with the appropriate partners to initiate. | Health and Wellbeing and Quality of the Public Realm | Totteridge Community Centre – New perimeter fencing and main entrance. Update: This has been agreed and will be funded by the High Wycombe Town Committee. | 31.03.27 |  |
| Improvements to Community Spaces | Improving a community space helps create a safer, cleaner, and more welcoming environment for everyone. It encourages positive use of the area, supports community pride, and can reduce anti-social behaviour. Well-maintained spaces also promote physical and mental wellbeing, contributing to a stronger and more connected community overall. In partnership with Buckinghamshire Highways and the Parks and Green Spaces team at Buckinghamshire Council, the Ward Partnership aims to deliver the works as detailed. | Health and Wellbeing Quality of the Public Realm | - Additional street light required for pedestrians. An additional small lantern has been requested by residents from the footpath by the bus stop in Totteridge Road across the Green to Hatters Lane. - Hicks Farm Wood, situated between Hatters Lane and St Hughes Avenue, was preserved through the efforts of a local group that successfully secured its status as a nature reserve within the Local Plan. However, as the group’s members are now getting older, there is a need to reinvigorate the initiative, particularly to encourage greater use and engagement from families. | 31.03.27 |  |
| Improvements to Community Spaces Cont’d | Improving a community space helps create a safer, cleaner, and more welcoming environment for everyone. It encourages positive use of the area, supports community pride, and can reduce anti-social behaviour. Well-maintained spaces also promote physical and mental wellbeing, contributing to a stronger and more connected community overall. In partnership with Buckinghamshire Highways and the Parks and Green Spaces team at Buckinghamshire Council, the Ward Partnership aims to deliver the works as detailed. | Health and Wellbeing Quality of the Public Realm | - Tadros Park - The play area and recreation ground require upgrades, including the replacement of a swing and the installation of a new zip wire. The perimeter fencing needs to be securely replaced where it borders the children’s play area. A large wooden park bench requires foundation repairs and refurbishment, while residents have reported a developing sinkhole nearby and the loss of an oak tree, along with eight additional trees and a hedge. Security lighting near the bridge also needs to be investigated following reported assaults, and the basketball court requires resurfacing. | 31.03.27 |  |
| Improvements to Community Spaces Cont’d | Improving a community space helps create a safer, cleaner, and more welcoming environment for everyone. It encourages positive use of the area, supports community pride, and can reduce anti-social behaviour. Well-maintained spaces also promote physical and mental wellbeing, contributing to a stronger and more connected community overall. In partnership with Buckinghamshire Highways and the Parks and Green Spaces team at Buckinghamshire Council, the Ward Partnership aims to deliver the works as detailed. | Health and Wellbeing Quality of the Public Realm | - Bowerdean - new noticeboards to be provided and fitted in the Ward. - As part of the Bowerdean crossroads improvement scheme, new signage should be installed on proper posts to clearly indicate Totteridge Road. The current sign is unattractive and attached to wire mesh fencing that is not owned by the Council. A new sign should also be placed on Bowerdean Road, or the existing one relocated as it is currently obscured by a large telegraph pole. In addition, any clutter attached to the existing street sign on Bowerdean Road should be removed. - Restoration of Cairnside Scrub, Totteridge. - To resolve fly tipping issue on Rowan Avenue service road. | 31.03.27 |  |
| Improvements to Community Spaces Cont’d | Improving a community space helps create a safer, cleaner, and more welcoming environment for everyone. It encourages positive use of the area, supports community pride, and can reduce anti-social behaviour. Well-maintained spaces also promote physical and mental wellbeing, contributing to a stronger and more connected community overall. In partnership with Buckinghamshire Highways and the Parks and Green Spaces team at Buckinghamshire Council, the Ward Partnership aims to deliver the works as detailed. | Health and Wellbeing Quality of the Public Realm | - Underwood Road - New bench and planting of bulbs. - Everest Estate – New Information Board required. - Wingate Avenue: To paint rails and plant bulbs. | 31.03.27 |  |
| Regeneration of Shopping Parades | The regeneration of shopping parades is important because it helps revitalise local economies, supports small businesses, and attracts more visitors to the area. Improved shops and public spaces create a more inviting environment, increasing footfall and community use. This can also enhance local pride, reduce vacancy rates, and make neighbourhoods feel safer and more vibrant, ultimately contributing to the overall wellbeing and sustainability of the community. The Ward Partnership will review this infrastructure enhancements and collaborate with the appropriate partners to initiate. | Health and Wellbeing and Quality of the Public Realm | Regeneration of shopping parades on Totteridge Drive and Quadrangle Parade | 2028 |  |
| Enhancement of East Wycombe Panoramic Walkway | Enhancing the East Wycombe Panoramic Walkway would improve health and wellbeing by encouraging outdoor activity, while creating a safer and more accessible route for all users. It would also enhance the quality of the public realm, strengthen community pride, support biodiversity, and increase the overall appeal of the area for both residents and visitors. | Health and Wellbeing and Quality of the Public Realm | The following is to be initiated: - Footpath resurfacing (100 metre length). - Directional signposts to local locations of interest, i.e., peace garden, ruins of Hospital of St John the Baptist (x4). - Graffiti removal (assumed 100 metre length). Other actions to be potentially delivered: - Interpretation/information boards with historical / local information (x6) (display information and artwork excluded, to be supplied) - Picnic benches at Lingfield Close, Gomm Valley and Tadros Park (x4) - Litter bins (x2) - Coin operated telescopes (x2) | 2028 |  |